## Slide 1
ACTIVE MOTION HR USE CASE
Onboarding - Offer Accepted
A trigger-driven workflow for identity creation, hardware fulfillment, training seat reservation, owner coordination, and day-one readiness.
TRIGGER
Offer accepted
START TARGET
Within 15 minutes
COMPLETION TARGET
Ready by T-2 business days
One accepted offer becomes one coordinated onboarding case.

## Slide 2
TRIGGER DEFINITION
The workflow starts from one trusted event.
The accepted-offer event becomes the control point for identity, equipment, training, communications, and audit.
Primary event
Candidate offer is marked Accepted and start date is confirmed in the ATS or HRIS.
Required fields
Legal name, preferred name, personal email, role, department, manager, location, start date, employment type, equipment profile, and training profile.
Duplicate protection
If an onboarding case already exists for candidate ID or employee ID, update the existing case instead of starting a second workflow.
Audit record
Store trigger timestamp, source-system event ID, actor, payload version, and workflow run ID.

## Slide 3
WORKFLOW PATH
Accepted offer to day-one readiness in seven moves.
The agent does the coordination work while humans handle exceptions and judgment calls.
01
Validate event
02
Stage worker profile
03
Create identity records
04
Request hardware
05
Reserve training
06
Notify owners
07
Track and escalate
Blocked items escalate before the start-date risk threshold, so readiness problems surface while they can still be solved.

## Slide 4
WORKSTREAM CHECKLIST
Every owner gets a clear deadline and scope.
The checklist makes handoffs visible: who owns the work, what must happen, and when it is due.
Workstream | Required actions | Owner | Due
Identity | Employee ID, directory, email, SSO, baseline access groups | IT / IAM | T-7
Hardware | Ticket, equipment profile, inventory, staging, shipment tracking | IT Fulfillment | T-5
Training | Orientation, compliance, security, role-specific sessions | L&D | T-5
Manager | First-week plan, buddy, first-day welcome | Hiring Manager | T-3
Workplace | Desk, badge, access, parking/transit, local support | Facilities | T-3
HR | Personal details, payroll packet, benefits path, policies, welcome email | HR Ops | T-2

## Slide 5
SYSTEMS AND INTEGRATIONS
The agent writes to the systems that already run onboarding.
Each integration has a defined write action and a human fallback path.
ATS / HRIS
Write action: Create or update onboarding case
Fallback: Manual HR Ops review
IAM / Directory
Write action: Create staged user and groups
Fallback: IAM ticket with fields
ITSM
Write action: Create fulfillment ticket
Fallback: Manual priority ticket
LMS
Write action: Enroll or reserve sessions
Fallback: L&D queue request
Calendar / Email
Write action: Send invites and updates
Fallback: Manual coordinator email

## Slide 6
EXCEPTION HANDLING
Automation handles the routine; escalation handles the risky.
Exceptions are expected paths with owners, not surprise failures.
Missing data: pause downstream writes, notify HR Ops, request completion.
Identity conflict: route to IAM for duplicate review before account creation.
Hardware unavailable: flag start-date risk and offer approved substitute equipment.
Training full: reserve the next available seat and alert L&D if mandatory.
Start date changes: recalculate due dates and notify all owners.

## Slide 7
ACCEPTANCE CRITERIA
Day-one ready means measurable, auditable, and visible.
A run is complete when status, ownership, system writes, escalation, and employee communications are all accounted for.
Done looks like
Every run has a unique case ID and visible status. Every downstream write is logged with timestamp, owner, result, and retry history. Items blocked within two business days of start date escalate to HR Ops and the hiring manager.
Human experience
The employee receives one coherent welcome message instead of disconnected system emails. The manager receives a concise readiness summary before the employee's first day.
Blank configuration fields
ATS/HRIS trigger name · workflow case queue · equipment profiles · training bundles · escalation distribution list · start-date risk threshold · reporting dashboard link